## Sheet1
Congruent Solutions Pvt. Ltd. |  | Service Change Management Plan | CR-#2024053100000343
Format Version No. 1.0
W.E.F 07.07.2022
Change Request Initiated By: Name: Sambavanathan A Cloud engineer - Azure |  |  | Date :01-06-2024
To be filled by Change Requester or Executive System Administration
Sl. No | Details of Change Required | Reasons for Change | Remarks
1 | Action Required: Security Patch Update in Pershing Prod servers
To Be filled by Team Lead - System Administration
Impact Analysis:
Impact Severity: | Medium
Guideline :
S. No. | Impact of the Change
| Services / Equipments | Stakeholders | Documents
1 | Pershing Prod servers | Product Team
Rollback Mechanism in case changes needs to be reverted - To be filled by Sr. Engineer
S. No. | List below the activities that needs to be performed to revert the changes
| Services / Equipments | Responsibility | Documents
1 | We could restore the VM with the previous snapshot if any booting issue. | 4D
Action Plan - Implementation
S.No. | Action Item description | Target Date | Responsibility | Status | Actual Date | Helpdesk ID
1 | Take a snapshot of the OS & Data disk for all the production servers | 01-06-2024 (10:00 AM to 5 PM) | Sambavanathan A (4D)
2 | Security Updates need to be done
3 | Once security Updates Done we need to restart all production VM's
Is change approved ?
Reason for rejection :
Completion Date : |  | 2024-06-01
| Prepared by | Reviewed By | Approved By
Signature
Name | Sambavanathan A | Arunkumar .A | Rajesh
Designation | Cloud Engineer | Program Manager | Manager-CSPL Appilcation Team
Date | 2024-06-01 | 2024-06-01
ss