## BCP Drill Plan
LFG - BCP DRILL
Testing Method: | DR Drill | Date: | 2024-06-25
|  | Start Time: | 14:30
|  | End Time: | 17:00
BCP Test Team: | 4D Team CSPL Team | 4D DR Team |  | 4D Escalation Team | CSPL DR Team
|  | Primary Contact: Name: Logeshwaran .M Email: logeshwaran.m@fourdtech.co.in Mob 8072749343 |  | Name: ArunKumar.A Email:arunkumar@fourdtech.co.in Mob: 9840711923 | Name: Rajesh Kumar.P Email: rajeshkumar.p@cspl.com Mob: 9840159769
|  | Seconday Contact: Name: Purushothaman G. Email: purushothaman@fourdtech.co.in Mob: 9080462110 |  | Name:Srinivasan.V Email:srinivasan.v@fourdtech.com Mob:9840711957
Process No | Recovery Steps | Estimated time(Mins) | Actual Time(Mins) | Responsibility | Verified By | Remarks
1 | Check for consistency of replication sets | 10 |  | 4D Team
Verify the completion of replication sets
2 | Failover the Replicated VM's in ASR |  |  | 4D Team
| Failover the Replicated LFGPDC VM | 60
Failover the Replicated LFGPrimarySQL VM
Failover the Replicated LFGWCF1 VM
Failover the Replicated LFGWEBAPP VM
3 | After Failover Process: |  |  | 4D Team
| Ensure all VMs UP & Running | 90
Ensure Private IP(Static) assigned for all VM’s in Azure portal
Assigning Public IP address to LFGWebAPP Server
Connect RDP Using Local User Account on LFGWebAPP Server
Allow Remote connection for domain user in LFGWebAPP Server
Ensure the Time Zone in EST
Manually assign Primary DNS for all the servers in Network Properties
Ensure DNS resolving on all the servers
Create a Storage account for Cloud Witness
Force Quorum in WFSC
Configure Cluster Quorum Settings to Default Quorum Configuration in WFSC
Ensure all AGs are running in Fail over Cluster Manager
Check the all AGs status primary in DB
Check the DB Connectivity
4 | Consistency Check |  |  | CSPL Team
| Test Availability of application and services | 60
Test Consistency of application and data
Results summarized and communicated to group
5 | Failback Process |  |  | 4D Team
| Clean up Failover Process in ASR | 60
Results summarized and communicated to group
| Total | 280